## Sheet1
ID | Name | Description | OwnedBy | Status
1 | Create Project Specification | Flush out notes from discussion in to more robust project specification document. | McGhee
2 | Pencil Mockups | Download Pencil Project https://pencil.evolus.vn/ | ALL | Complete
3 | Create ER Diagram | Create Entity Relationship Diagram for data objects. Show Relationships between objects, identify relationship type (many to many, many to one). MS Visio preferred tool. | Rakeem | Complete
4 | Create Collect Sample Mockup | Using Pencil create a Collect Sample Mockup | Adithya
5 | Experiment with ASP.NET MVC | Create a new project in ASP.NET MVC that does something. | ALL
6 | Create a Working Sample Entry Form | In ASP.NET MVC using SQL data file - present back to group. | Austin
7 | Create github project | Create a github project or project documentation and source files. - demonstrate how to use. | Austin
| Explore Building Related Data | Identify best approach to build related data in ASP.NET MVC Project. Samples -> Tests -> Results
| Build Mockups for Sample Data Manager | Using Pencil Create Sample Data Manager UI Mockups for functionality identified in User Stories. | Adithya
| Build Models for Data Objects | Build Models for Data Objects identified as of 9/22 | Rakeem
Develop Login / Authentication
Develop UI Navigation
| Identify Technique to Combine Multiple Page Functions |  | Austin
| Example Data For Project | Example data to aid in Development of EM Tracker - things such as locations and types for meta data | McGhee
| Creating Custom Bootstrap Style Sheet | Create a custom style sheet to give the project a unique look and feel.